| Ex No: 02 Date: | Scheduling of Project with PERT and CPM Techniques |
| --- | --- |

Aim

To estimate the project completion time by creating a project schedule, defining task dependencies, generating the CPM and PERT network diagrams, assigning resources and costs, and calculating the overall project duration using ProjectLibre

Algorithm

- Open ProjectLibre.

- Create a new project.

- Enter project name and start date.

- Create project activities with durations.

- Define predecessor relationships.

- Generate Gantt Chart.

- Generate Network Diagram (PERT/CPM).

- Create Resource Sheet.

- Assign resource costs.

- Allocate resources.

- View Project Summary and Cost Report.

- Save the project

Procedure

Step 1: Create a New Project

- Open ProjectLibre.

- Click File → New.

- Enter:

  - Project Name: Software Project Scheduling

  - Manager: Your Name

  - Start Date: Select today's date.

- Click OK.

Step 2: Enter Project Activities

In the Gantt Chart, enter the following activities:

| Task Name | Duration |
| --- | --- |
| Requirement Gathering | 2d |
| Feasibility Analysis | 3d |
| UI/UX Design | 4d |
| Database Development | 5d |
| Application Development | 6d |
| System Testing | 3d |
| Bug Resolution | 2d |
| Project Deployment | 1d |

Step 3: Enter Predecessors

In the Predecessors column, enter:

| Task | Predecessor |
| --- | --- |
| Requirement Gathering | - |
| Feasibility Analysis | 1 |
| UI/UX Design | 2 |
| Database Development | 3 |
| Application Development | 4 |
| System Testing | 5 |
| Bug Resolution | 6 |
| Project Deployment | 7 |

ProjectLibre will automatically schedule the project.

Step 4: View the Gantt Chart

After entering the tasks and predecessors:

- The Gantt Chart will be generated automatically on the right side.

- This shows the start date, finish date, and duration of each activity.

Step 5: View the Network Diagram (PERT/CPM)

- Click View.

- Select Network Diagram.

ProjectLibre automatically creates the PERT/CPM Network Diagram showing the sequence of project activities.

Step 6: Create Resources

Go to View → Resource Sheet and enter:

| Resource Name | Standard Rate |
| --- | --- |
| Arun Kumar | ₹2000/day |
| Priya Sharma | ₹1800/day |
| Karthik Raj | ₹2500/day |
| Nisha Devi | ₹2200/day |
| Rahul Verma | ₹2700/day |
| Deepika S | ₹2100/day |
| Ajay Kumar | ₹1900/day |
| Meena R | ₹2300/day |

Step 7: Assign Resources

Return to the Gantt Chart.

Assign the resources:

| Task | Resource |
| --- | --- |
| Requirement Gathering | Arun Kumar |
| Feasibility Analysis | Priya Sharma |
| UI/UX Design | Karthik Raj |
| Database Development | Nisha Devi |
| Application Development | Rahul Verma |
| System Testing | Deepika S |
| Project Deployment | Meena R |
| Bug Resolution | Ajay Kumar |

Step 8: View Project Summary

After assigning resources:

- Click Project or Reports (depending on your ProjectLibre version).

- View:

  - Total Duration

  - Total Cost

  - Resource Allocation

Observation:

Project Duration: 26 Days 208 Hours

Requirement Gathering → Feasibility Analysis → UI/UX Design → Database Development → Application Development → System Testing → Bug Resolution → Project Deployment

Critical Path:

Result:

The project schedule was successfully created using PERT and CPM techniques in ProjectLibre. The software automatically generated the Gantt Chart and Network Diagram, identified the critical path, and estimated the project completion time of 26 days (208 hours).